## Sheet1
To use this form: Enter the trip date in cell H1. Task due dates will be autocompleted based on the intended trip date. RED Tasks are Show Stoppers if not completed. | Troop 272 Overnight Planning Calendar |  |  |  | Enter Trip Date: | 2025-02-12
Action to be Taken | Days Before Outing | Date Assigned | Task Assigned To | Is It Done (Y/N)?
Boy Trip Leader Recruited | 60 | 2024-12-14
Adult Trip Leader Recruited | 60 | 2024-12-14
2-Deep Leadership Confirmed | 55 | 2024-12-19
Initial Planning Meeting Held | 55 | 2024-12-19
Campsite/ Event Site Reserved | 50 | 2024-12-24
Costs Determined | 50 | 2024-12-24
Event Promotion Begins via email | 45 | 2024-12-29
Permission Slips Sent Out | 45 | 2024-12-29
Permission Slips and Fees Collected | 30 | 2024-12-19
Event Promotion Ends via email | 30 | 2025-01-13
Trip Roster Completed | 30 | 2025-01-13
Event Agenda Approved by PLC | 25 | 2025-01-18
Event Agenda and Program Finalized | 21 | 2025-01-22
Medical Forms Confirmed | 21 | 2025-01-22
Trip meeting for menu & duties | 14 | 2025-01-29
Packing list(s) goes out via email | 14 | 2025-01-29
Check For Hazardous Weather | 5 | 2025-02-07
Patrol Grubmasters Shop for Food | 2 | 2025-02-10
Event Begins | 0 | 2025-02-12
Review Event | 15 after | 2025-02-27
Events in RED Are show stoppers if not completed
Formulas:
Date Assigned = (H1 -[Days Before Outing])
Date Assigned = H1-[Days Before Outing]