## Sheet1
Troop 272 Overnight Planning Calendar
Action to be Taken | Days Before Outing | Date Assigned | Task Assigned To | Is It Done (Y/N)?
Boy Trip Leader Recruited | 60
Adult Trip Leader Recruited | 60
2-Deep Leadership Confirmed | 55
Initial Planning Meeting Held | 55
Campsite/ Event Site Reserved | 50
Costs Determined | 50
Event Promotion Begins via email | 45
Permission Slips Sent Out | 45
Permission Slips and Fees Collected | 30
Event Promotion Ends via email | 30
Roster Completed | 30
Event Agenda and Program Finalized | 21
Medical Forms Confirmed | 21
Trip meeting for menu & duties | 14
Tour Permit Filed (by adult leader) | 14
Packing list(s) goes out via email | 14
Check Weather | 5
Patrol Grubmasters Shop for Food | 2
Event Begins | 0
Review Event | 15 after
Events in RED Are show stoppers if not completed